## Requirements
Section | Subsection | Category | Req ID | Description | Spec | Phase | Status | Comments
INFRASTRUCTURE LAYER | Language Support & Editor | INFRASTRUCTURE LAYER > Language Support & Editor | INF-001 | Monaco editor integration with syntax highlighting | 3.1.1 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/CodeViewer.tsx + src-ui/monaco-setup.ts. Workers configured. Theme applied.
INFRASTRUCTURE LAYER | Language Support & Editor | INFRASTRUCTURE LAYER > Language Support & Editor | INF-002 | Tree-sitter for AST parsing (10+ languages: Python, JS, TS, Rust, Go, Java, C, C++, Ruby, PHP, Swift, Kotlin) | 3.1.1 | Phase 1 - MVP | ✅ | COMPLETE: 11 parser modules in src-tauri/src/gnn/parser_*.rs. All languages supported.
INFRASTRUCTURE LAYER | Language Support & Editor | INFRASTRUCTURE LAYER > Language Support & Editor | INF-003 | Language Server Protocol integration (autocomplete, hover, diagnostics) | 3.1.1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No LSP integration found. Would need tower-lsp or similar crate.
INFRASTRUCTURE LAYER | Language Support & Editor | INFRASTRUCTURE LAYER > Language Support & Editor | INF-004 | LLM-driven code completion (primary tier, context-aware) | 3.1.1.1 | Phase 1 - MVP | 🟡 | PARTIAL: LLM orchestrator exists (src-tauri/src/llm/). Monaco completion provider NOT wired up.
INFRASTRUCTURE LAYER | Language Support & Editor | INFRASTRUCTURE LAYER > Language Support & Editor | INF-005 | Dependency graph-powered suggestions (secondary tier, project-aware) | 3.1.1.1 | Phase 1 - MVP | 🟡 | PARTIAL: GNN query exists. Monaco completion provider integration MISSING.
INFRASTRUCTURE LAYER | Language Support & Editor | INFRASTRUCTURE LAYER > Language Support & Editor | INF-006 | Static keyword/snippet completion (fallback tier, instant) | 3.1.1.1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No static snippet library found in Monaco setup.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-001 | Track file-to-file dependencies (import/include relationships) | 3.1.2 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/gnn/graph.rs tracks imports. EdgeType::Imports implemented.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-002 | Track code symbol dependencies (function calls, class usage, methods) | 3.1.2 | Phase 1 - MVP | ✅ | COMPLETE: EdgeType::Calls, EdgeType::Uses, EdgeType::Defines. Function/class tracking in all parsers.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-003 | Track exact package versions as separate nodes (numpy==1.24.0 vs 1.26.0) | 3.1.2 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: Package nodes don't include version info. Critical gap for version conflict detection.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-004 | Track tool dependencies (webpack→babel, test frameworks, linters) | 3.1.2 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No tool chain tracking found. Would need separate node type.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-005 | Track package-to-file mapping (which files use which packages) | 3.1.2 | Phase 1 - MVP | 🟡 | PARTIAL: Import tracking exists but not aggregated at package level. Query layer needed.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-006 | Track user-to-file (active work tracking) | 3.1.2 | Phase 2A - Post-MVP | ⚪ | PLANNED: Phase 2A feature for team coordination.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-007 | Track Git checkout level modifications | 3.1.2 | Phase 2A - Post-MVP | ⚪ | PLANNED: Phase 2A feature with Git coordination branch.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-008 | Track external API endpoints as nodes | 3.1.2 | Phase 3 - Post-MVP | ⚪ | PLANNED: Phase 3 enterprise automation feature.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-009 | Track method chains (df.groupby().agg() granularity) | 3.1.2 | Phase 3 - Post-MVP | ⚪ | PLANNED: Phase 3 deep tracking feature.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-010 | HNSW semantic indexing (all-MiniLM-L6-v2, 384-dim embeddings) | 3.1.2 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/gnn/hnsw_index.rs with hnsw_rs crate. Embeddings stored in nodes.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-011 | Bidirectional graph edges (reverse queries) | 3.1.2 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/gnn/graph.rs uses petgraph DiGraph with bidirectional edge tracking.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-012 | Fast incremental updates (<1ms per edge) | 3.1.2 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/gnn/incremental.rs with file change tracking and delta updates.
INFRASTRUCTURE LAYER | Dependency Graph (Core Differentiator) | INFRASTRUCTURE LAYER > Dependency Graph (Core Differentiator) | DEP-013 | Breaking change detection (signature changes, removed functions) | 3.1.2 | Phase 1 - MVP | 🟡 | PARTIAL: Function signature tracking exists. Automatic breaking change detection logic INCOMPLETE.
INFRASTRUCTURE LAYER | Extended Dependency Features | INFRASTRUCTURE LAYER > Extended Dependency Features | EXT-001 | Dependency-aware file locking (proactive conflict prevent) | 3.1.3 | Phase 2A - Post-MVP | ⚪ | PLANNED: Requires Tier 2 (sled) storage + Team of Agents architecture.
INFRASTRUCTURE LAYER | Extended Dependency Features | INFRASTRUCTURE LAYER > Extended Dependency Features | EXT-002 | Proactive conflict detection (before code generation) | 3.1.3 | Phase 2A - Post-MVP | ⚪ | PLANNED: Phase 2A with Git coordination branch.
INFRASTRUCTURE LAYER | Extended Dependency Features | INFRASTRUCTURE LAYER > Extended Dependency Features | EXT-003 | Work visibility UI (show active file editors) | 3.1.3 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: UI component missing. Would show real-time file edit status.
INFRASTRUCTURE LAYER | Extended Dependency Features | INFRASTRUCTURE LAYER > Extended Dependency Features | EXT-004 | Developer activity tracking (who/what/when audit trail) | 3.1.3 | Phase 2A - Post-MVP | ⚪ | PLANNED: Phase 2A team collaboration feature.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-001 | Block database (SQLite with full-text search FTS5) | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No YDoc SQLite schema found. Critical foundation missing.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-002 | 12 document types (Requirements, ADR, Architecture, Tech Spec, Plan, Guides, Test Plan/Results, Change/Decision Log) | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: Document type system not created.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-003 | Graph-native documentation (traceability edges: traces_to, implements, realized_in, tested_by, documents, has_issue) | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No YDoc edge types in graph. Extension needed.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-004 | MASTER.ydoc folder index files with ordering/metadata | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: File structure and generation logic missing.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-005 | Smart test archiving (>30 days, keep summary stats) | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: Test result retention policy not implemented.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-006 | Monaco/nteract rendering for .ydoc files | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: .ydoc file type not registered in Monaco.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-007 | Confluence bidirectional sync via MCP server | 3.1.4, SPEC-ydoc Section 14 | Phase 2 - Post-MVP | ⚪ | PLANNED: Phase 2 enterprise documentation integration.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-008 | Document version control (timestamps, change metadata) | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: Versioning system not created.
INFRASTRUCTURE LAYER | YDoc Documentation System | INFRASTRUCTURE LAYER > YDoc Documentation System | YDOC-009 | Yantra metadata fields (yantra_id, linked_nodes, tags, status, etc.) | 3.1.4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: Metadata schema not defined.
INFRASTRUCTURE LAYER | Unlimited Context Solution | INFRASTRUCTURE LAYER > Unlimited Context Solution | CTX-001 | Hierarchical context strategy (current msg, recent turns, direct deps, transitive deps, semantic similarity) | 3.1.5 | Phase 1 - MVP | 🟡 | PARTIAL: src-tauri/src/llm/context_builder.rs exists. Hierarchical priority logic INCOMPLETE.
INFRASTRUCTURE LAYER | Unlimited Context Solution | INFRASTRUCTURE LAYER > Unlimited Context Solution | CTX-002 | Dynamic context assembly (relevance + token budget based) | 3.1.5 | Phase 1 - MVP | 🟡 | PARTIAL: Context builder assembles context. Token budget tracking INCOMPLETE.
INFRASTRUCTURE LAYER | Unlimited Context Solution | INFRASTRUCTURE LAYER > Unlimited Context Solution | CTX-003 | Compression techniques (summarization, deduplication, truncation) | 3.1.5 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No compression logic found. Would need LLM-based summarization.
INFRASTRUCTURE LAYER | Unlimited Context Solution | INFRASTRUCTURE LAYER > Unlimited Context Solution | CTX-004 | Token budget management (track usage across context levels) | 3.1.5 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No token counting logic found.
INFRASTRUCTURE LAYER | Unlimited Context Solution | INFRASTRUCTURE LAYER > Unlimited Context Solution | CTX-005 | LLM-agnostic support (Claude, GPT-4, Qwen, any model with context limits) | 3.1.5 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/llm/orchestrator.rs supports multiple models via config.
INFRASTRUCTURE LAYER | Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | INFRASTRUCTURE LAYER > Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | CODEX-001 | GraphSAGE architecture (1024-dim embeddings, 150M parameters) | 3.1.6 | MVP Stretch / Phase 2 | ⚪ | STRETCH GOAL: Deferred to post-MVP. System works without Codex using LLM-only approach.
INFRASTRUCTURE LAYER | Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | INFRASTRUCTURE LAYER > Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | CODEX-002 | Pattern storage (learned code patterns, bug patterns, test patterns) | 3.1.6 | MVP Stretch / Phase 2 | ⚪ | STRETCH GOAL: Deferred to post-MVP. Template patterns can use existing GNN + embeddings.
INFRASTRUCTURE LAYER | Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | INFRASTRUCTURE LAYER > Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | CODEX-003 | Continuous learning (from bugs, tests, LLM mistakes, manual edits, code reviews) | 3.1.6 | MVP Stretch / Phase 2 | ⚪ | STRETCH GOAL: Deferred to post-MVP. Learning through LLM consultation sufficient for MVP.
INFRASTRUCTURE LAYER | Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | INFRASTRUCTURE LAYER > Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | CODEX-004 | 15ms inference (CPU), 5ms (GPU) for pattern matching | 3.1.6 | MVP Stretch / Phase 2 | ⚪ | STRETCH GOAL: Deferred to post-MVP. LLM inference time acceptable for MVP.
INFRASTRUCTURE LAYER | Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | INFRASTRUCTURE LAYER > Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | CODEX-005 | Cost optimization (96% LLM reduction after 12 months through learned patterns) | 3.1.6 | MVP Stretch / Phase 2 | ⚪ | STRETCH GOAL: Long-term optimization. MVP focuses on correctness, not cost optimization.
INFRASTRUCTURE LAYER | Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | INFRASTRUCTURE LAYER > Yantra Codex (GNN Intelligence Layer) - MVP STRETCH GOAL | CODEX-006 | Cloud Codex (opt-in shared learning across Yantra installations) | 3.1.6 | Phase 3 - Post-MVP | ⚪ | PLANNED: Phase 3 community-driven improvements, dependent on Codex implementation.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-001 | Multi-tier storage (Tier 0 Cloud, Tier 1 petgraph+SQLite, Tier 2 sled, Tier 3 TOML, Tier 4 HashMap/moka, Codex separate SQLite+HNSW) | 3.1.7 | Phase 1 MVP (1,3,4), Phase 2A (Tier 2), 2B (Tier 0), Codex (Stretch) | 🟡 | PARTIAL: Tier 1 (petgraph+SQLite) exists. Tier 3 (TOML) exists. Tier 0,2,4 MISSING. Codex deferred (stretch goal).
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-002 | Tier 1 SQLite (dependency graph, metadata, config, WAL mode, connection pooling) | 3.1.7 | Phase 1 - MVP | 🟡 | PARTIAL: SQLite for graph persistence exists. WAL mode NOT enabled. Connection pooling NOT implemented.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-003 | Tier 2 sled (agent state, file locks, task queue for multi-agent) | 3.1.7 | Phase 2A - Post-MVP | ⚪ | PLANNED: Phase 2A Team of Agents requirement.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-004 | Tier 3 Vector DB (semantic search, pattern matching, similarity queries) | 3.1.7 | Phase 1 - MVP | ✅ | COMPLETE: HNSW indexing in src-tauri/src/gnn/hnsw_index.rs with hnsw_rs crate.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-005 | Tier 4 File System (code files, assets, temporary data) | 3.1.7 | Phase 1 - MVP | ✅ | COMPLETE: Standard file operations in src-tauri/src/agent/file_ops.rs.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-006 | Tier 0 Cloud Graph DB (shared dependency graph for team coordination) | 3.1.7 | Phase 2B - Post-MVP | ⚪ | PLANNED: Phase 2B PostgreSQL + Redis for cross-machine conflict prevention.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-007 | De-duplication index (prevent duplicate file/function/doc creation) | 3.1.7 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: Content-addressable storage not implemented. Needed for creation validation service.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-008 | WAL mode for SQLite (Write-Ahead Logging) | 3.1.7 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: CRITICAL - SQLite not using WAL mode. Required for concurrent reads/writes.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-009 | Connection pooling (reuse DB connections, max 10) | 3.1.7 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No connection pool (r2d2 or deadpool). Single connection per operation.
INFRASTRUCTURE LAYER | Storage Architecture | INFRASTRUCTURE LAYER > Storage Architecture | STOR-010 | Data archiving (test results >30 days, logs >90 days) | 3.1.7 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No archiving policy or automation.
INFRASTRUCTURE LAYER | Browser Integration | INFRASTRUCTURE LAYER > Browser Integration | BROW-001 | CDP protocol support (Chrome DevTools Protocol) | 3.1.8 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/browser/ with chromiumoxide crate. CDP client implemented.
INFRASTRUCTURE LAYER | Browser Integration | INFRASTRUCTURE LAYER > Browser Integration | BROW-002 | System browser usage (user's Chrome/Chromium/Edge, not bundled) | 3.1.8 | Phase 1 - MVP | ✅ | COMPLETE: chromiumoxide connects to system Chrome.
INFRASTRUCTURE LAYER | Browser Integration | INFRASTRUCTURE LAYER > Browser Integration | BROW-003 | Browser validation workflow (launch, navigate, execute, capture) | 3.1.8 | Phase 1 - MVP | 🟡 | PARTIAL: Basic launch/navigate exists. Full validation workflow INCOMPLETE.
INFRASTRUCTURE LAYER | Browser Integration | INFRASTRUCTURE LAYER > Browser Integration | BROW-004 | Console error capture (monitor JavaScript errors) | 3.1.8 | Phase 1 - MVP | 🟡 | PARTIAL: CDP console events available. Error collection logic INCOMPLETE.
INFRASTRUCTURE LAYER | Browser Integration | INFRASTRUCTURE LAYER > Browser Integration | BROW-005 | Network monitoring (API calls, failures, performance) | 3.1.8 | Phase 1 - MVP | 🟡 | PARTIAL: CDP network events available. Monitoring logic INCOMPLETE.
INFRASTRUCTURE LAYER | Browser Integration | INFRASTRUCTURE LAYER > Browser Integration | BROW-006 | Screenshot capture (visual verification at key steps) | 3.1.8 | Phase 1 - MVP | 🟡 | PARTIAL: Screenshot API available. Integration with validation workflow INCOMPLETE.
INFRASTRUCTURE LAYER | Browser Integration | INFRASTRUCTURE LAYER > Browser Integration | BROW-007 | Self-healing triggers (auto-fix production browser errors) | 3.1.8 | Phase 4 - Post-MVP | ⚪ | PLANNED: Phase 4 Maintenance State Machine feature.
INFRASTRUCTURE LAYER | Architecture View System | INFRASTRUCTURE LAYER > Architecture View System | ARCH-001 | Agent-driven generation (auto-generate from code/intent/requirements) | 3.1.9 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/architecture/ with generation, storage, CRUD operations.
INFRASTRUCTURE LAYER | Architecture View System | INFRASTRUCTURE LAYER > Architecture View System | ARCH-002 | Deviation detection (detect code drift from architecture) | 3.1.9 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/architecture/governance.rs with deviation detection.
INFRASTRUCTURE LAYER | Architecture View System | INFRASTRUCTURE LAYER > Architecture View System | ARCH-003 | Rule of 3 versioning (current + 3 most recent = 4 total) | 3.1.9 | Phase 2 - Post-MVP | ⚪ | PLANNED: Version history not yet implemented.
INFRASTRUCTURE LAYER | Architecture View System | INFRASTRUCTURE LAYER > Architecture View System | ARCH-004 | Human approval gate (user approval before architecture changes) | 3.1.9 | Phase 1 - MVP | 🟡 | PARTIAL: Approval workflow exists in agent. UI confirmation INCOMPLETE.
INFRASTRUCTURE LAYER | Architecture View System | INFRASTRUCTURE LAYER > Architecture View System | ARCH-005 | Continuous alignment (monitor code changes, update architecture) | 3.1.9 | Phase 1 - MVP | 🟡 | PARTIAL: Architecture updater exists. Continuous monitoring automation INCOMPLETE.
INFRASTRUCTURE LAYER | Architecture View System | INFRASTRUCTURE LAYER > Architecture View System | ARCH-006 | Visual representation (diagrams with components and connections) | 3.1.9 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/src/components/ArchitectureView.tsx with Mermaid diagram rendering.
INFRASTRUCTURE LAYER | Security Infrastructure | INFRASTRUCTURE LAYER > Security Infrastructure | SEC-001 | Semgrep integration (OWASP Top 10: SQL injection, XSS, CSRF, etc.) | 3.1.12 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/security/scanner.rs with Semgrep integration.
INFRASTRUCTURE LAYER | Security Infrastructure | INFRASTRUCTURE LAYER > Security Infrastructure | SEC-002 | Secrets detection (API keys, passwords, tokens via TruffleHog patterns) | 3.1.12 | Phase 1 - MVP | 🟡 | PARTIAL: Basic pattern matching exists. Full TruffleHog-level detection INCOMPLETE.
INFRASTRUCTURE LAYER | Security Infrastructure | INFRASTRUCTURE LAYER > Security Infrastructure | SEC-003 | Dependency vulnerability scanning (CVE database) | 3.1.12 | Phase 1 - MVP | 🟡 | PARTIAL: CVE checking logic exists. Database integration INCOMPLETE.
INFRASTRUCTURE LAYER | Security Infrastructure | INFRASTRUCTURE LAYER > Security Infrastructure | SEC-004 | License compliance (verify license compatibility) | 3.1.12 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No license checking logic found.
INFRASTRUCTURE LAYER | Security Infrastructure | INFRASTRUCTURE LAYER > Security Infrastructure | SEC-005 | Auto-fix patterns (parameterized queries, escaping, env vars) | 3.1.12 | Phase 1 - MVP | 🟡 | PARTIAL: Some fix patterns exist. Comprehensive auto-fix library INCOMPLETE.
INFRASTRUCTURE LAYER | Security Infrastructure | INFRASTRUCTURE LAYER > Security Infrastructure | SEC-006 | Parallel scanning (4 workers concurrent) | 3.1.12 | Phase 1 - MVP | 🟡 | PARTIAL: Async/await structure supports parallelism. Explicit parallel execution MISSING.
INFRASTRUCTURE LAYER | Security Infrastructure | INFRASTRUCTURE LAYER > Security Infrastructure | SEC-007 | Severity blocking (block Critical/High, warn Medium, log Low) | 3.1.12 | Phase 1 - MVP | 🟡 | PARTIAL: Severity classification exists. Blocking logic INCOMPLETE.
AGENTIC LAYER | Agentic Framework (Four Pillars) | AGENTIC LAYER > Agentic Framework (Four Pillars) | AG-001 | PERCEIVE primitives (file ops, dependency analysis, code intelligence, test/validation, environment sensing) | 3.2, 3.3.1 | Phase 1 - MVP | ✅ | COMPLETE: Multiple modules in src-tauri/src/agent/ - file_ops, validation, dependencies, affected_tests, etc.
AGENTIC LAYER | Agentic Framework (Four Pillars) | AGENTIC LAYER > Agentic Framework (Four Pillars) | AG-002 | REASON primitives (pattern matching, risk assessment, architectural analysis, LLM consult, confidence score) | 3.2, 3.3.2 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/agent/confidence.rs, project_initializer.rs (impact analysis), conflict_detector
AGENTIC LAYER | Agentic Framework (Four Pillars) | AGENTIC LAYER > Agentic Framework (Four Pillars) | AG-003 | ACT primitives (code gen, file manipulation, test execution, deployment, browser automation, Git ops) | 3.2, 3.3.3 | Phase 1 - MVP | ✅ | COMPLETE: orchestrator.rs, file_editor.rs, deployment.rs, packaging.rs, Git operations implemented
AGENTIC LAYER | Agentic Framework (Four Pillars) | AGENTIC LAYER > Agentic Framework (Four Pillars) | AG-004 | LEARN primitives (pattern capture, feedback processing, Codex updates, analytics) | 3.2, 3.3.4 | MVP Stretch / Phase 2 | ⚪ | STRETCH GOAL: Deferred with Yantra Codex. MVP uses LLM retry/feedback without explicit learning.
AGENTIC LAYER | Agentic Framework (Four Pillars) | AGENTIC LAYER > Agentic Framework (Four Pillars) | AG-005 | Cross-cutting primitives (state management, context management, communication, error handling) | 3.2, 3.3.5 | Phase 1 - MVP | ✅ | COMPLETE: state.rs (state machine), llm/context.rs (context), error types throughout, status_emitter for events
AGENTIC LAYER | Unified Tool Interface (UTI) | AGENTIC LAYER > Unified Tool Interface (UTI) | UTI-001 | Protocol abstraction (single API abstracting LSP, MCP, DAP, Builtin) | 3.3.0 | Phase 1 - MVP | 🟡 | PARTIAL: MCP implemented (src-tauri/src/git/mcp.rs). LSP/DAP abstraction layer MISSING.
AGENTIC LAYER | Unified Tool Interface (UTI) | AGENTIC LAYER > Unified Tool Interface (UTI) | UTI-002 | Protocol selection framework (guidelines for Builtin vs MCP vs LSP vs DAP) | 3.3.0 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No unified decision framework. Tool selection ad-hoc.
AGENTIC LAYER | Unified Tool Interface (UTI) | AGENTIC LAYER > Unified Tool Interface (UTI) | UTI-003 | LSP support (Language Server Protocol for code intelligence) | 3.3.0 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No LSP client. Would need tower-lsp integration.
AGENTIC LAYER | Unified Tool Interface (UTI) | AGENTIC LAYER > Unified Tool Interface (UTI) | UTI-004 | MCP support (Model Context Protocol for external tool integrations) | 3.3.0 | Phase 1 - MVP | ✅ | COMPLETE: Git MCP implemented in src-tauri/src/git/mcp.rs with MCP-compliant operations.
AGENTIC LAYER | Unified Tool Interface (UTI) | AGENTIC LAYER > Unified Tool Interface (UTI) | UTI-005 | DAP support (Debug Adapter Protocol for debugging) | 3.3.0 | Phase 2 - Post-MVP | ⚪ | PLANNED: Phase 2 interactive debugging feature.
AGENTIC LAYER | Unified Tool Interface (UTI) | AGENTIC LAYER > Unified Tool Interface (UTI) | UTI-006 | Builtin tools (core tools implemented in Rust for performance) | 3.3.0 | Phase 1 - MVP | ✅ | COMPLETE: Most tools are builtin Rust implementations (file ops, GNN, testing, security, etc.).
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-001 | Primary LLM config (Claude Sonnet 4 default, user-configurable) | 3.4.1 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/llm/config.rs with LLMConfig struct, primary_provider field.
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-002 | Secondary LLM config (GPT-4 Turbo fallback, user-configurable) | 3.4.1 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/llm/config.rs with secondary_provider Option field.
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-003 | Consultation strategy (multi-LLM consultation after 2 failures) | 3.4.1 | Phase 1 - MVP | 🟡 | PARTIAL: Failover logic exists. Multi-LLM consultation (parallel queries) NOT implemented.
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-004 | Circuit breaker (automatic fallback on repeated failures) | 3.4.1 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/llm/orchestrator.rs with CircuitBreaker struct, Open/Closed/HalfOpen states
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-005 | Response caching (cache identical inputs) | 3.4.1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No caching layer found. Would need moka or similar.
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-006 | Failover sequence (Primary → Retry → Secondary → Consultation → User) | 3.4.1 | Phase 1 - MVP | 🟡 | PARTIAL: Primary → Secondary implemented. Consultation step MISSING.
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-007 | Cost tracking (track token usage and costs per operation) | 3.4.1 | Phase 1 - MVP | 🟡 | PARTIAL: Token counting exists in llm/tokens.rs. Cost calculation/tracking INCOMPLETE.
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-008 | Model allowlist (configurable list of allowed models) | 3.4.1 | Phase 1 - MVP | 🟡 | PARTIAL: Models defined in llm/models.rs. Allowlist enforcement MISSING.
AGENTIC LAYER | LLM Orchestration | AGENTIC LAYER > LLM Orchestration | LLM-009 | OpenRouter integration (unified API for multiple models with pricing) | 3.4.1 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/llm/openrouter.rs with full OpenRouter client implementation.
AGENTIC LAYER | Multi-LLM Team Orchestration (Phase 2) | AGENTIC LAYER > Multi-LLM Team Orchestration (Phase 2) | TEAM-001 | Lead agent (coordinator for task decomposition and assignment) | 3.4.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Phase 2A Team of Agents architecture.
AGENTIC LAYER | Multi-LLM Team Orchestration (Phase 2) | AGENTIC LAYER > Multi-LLM Team Orchestration (Phase 2) | TEAM-002 | Specialist agents (Coding, Architecture, Testing, Documentation, UX with configurable LLMs) | 3.4.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Agent specialization in Phase 2A.
AGENTIC LAYER | Multi-LLM Team Orchestration (Phase 2) | AGENTIC LAYER > Multi-LLM Team Orchestration (Phase 2) | TEAM-003 | Agent coordination (A2A protocol for inter-agent communication) | 3.4.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Agent-to-agent protocol specification needed.
AGENTIC LAYER | Multi-LLM Team Orchestration (Phase 2) | AGENTIC LAYER > Multi-LLM Team Orchestration (Phase 2) | TEAM-004 | Parallel execution (multiple agents working on different files simultaneously) | 3.4.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: 3-10x speedup target with parallel agents.
AGENTIC LAYER | Multi-LLM Team Orchestration (Phase 2) | AGENTIC LAYER > Multi-LLM Team Orchestration (Phase 2) | TEAM-005 | Agent instruction files (per-agent configuration in .yantra/agents/) | 3.4.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Agent customization via instruction files.
AGENTIC LAYER | Multi-LLM Team Orchestration (Phase 2) | AGENTIC LAYER > Multi-LLM Team Orchestration (Phase 2) | TEAM-006 | Performance targets (<30s Lead overhead, <5ms file locks, <100ms messages) | 3.4.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Performance benchmarks for Phase 2A.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-001 | ArchitectureGeneration state (generate/import project architecture) | 3.4.2.1 State 1 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/architecture/ and agent/project_initializer.rs with architecture generation
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-002 | ArchitectureReview state (human approval gate for arch changes) | 3.4.2.1 State 2 | Phase 1 - MVP | 🟡 | PARTIAL: Architecture governance exists. Human approval UI workflow INCOMPLETE.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-003 | DependencyAssessment state (analyze package/tool requirements, CVE scan, web search) | 3.4.2.1 State 3 | Phase 1 - MVP | 🟡 | PARTIAL: Dependency analysis exists. CVE scanning partial. Web search integration MISSING.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-004 | TaskDecomposition state (break feature into atomic tasks with file mappings) | 3.4.2.1 State 4 | Phase 1 - MVP | 🟡 | PARTIAL: Task decomposition logic exists in orchestrator. File mapping to tasks INCOMPLETE.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-005 | DependencySequencing state (topological sort for correct execution order) | 3.4.2.1 State 5 | Phase 1 - MVP | 🟡 | PARTIAL: GNN provides dependency graph. Topological sort for task ordering NOT implemented.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-006 | ConflictCheck state (query active work visibility MVP, file locks Phase 2A) | 3.4.2.1 State 6 | Phase 1 MVP / Phase 2A | 🟡 | PARTIAL: Conflict detection exists. Work visibility UI MISSING. File locks Phase 2A.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-007 | PlanGeneration state (create execution plan with estimates and priorities) | 3.4.2.1 State 7 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No explicit plan generation state. Would need task estimation and prioritization logic.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-008 | BlastRadiusAnalysis state (analyze impact before execution - P0 feature) | 3.4.2.1 State 8 | Phase 1 - MVP | 🟡 | PARTIAL: Impact analysis exists in project_initializer. Full blast radius with GNN traversal INCOMPLETE.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-009 | PlanReview state (optional approval for >5 tasks or multi-file changes) | 3.4.2.1 State 9 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No plan review state or UI prompt.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-010 | EnvironmentSetup state (create venv, install deps, validate setup) | 3.4.2.1 State10 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/agent/environment.rs and dependencies.rs with venv creation and dep installation
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-011 | FileLockAcquisition state (acquire file locks before editing) | 3.4.2.1 State11 | Phase 2A - Post-MVP | ⚪ | PLANNED: Deferred to Phase 2A Team of Agents with Tier 2 (sled) storage.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-012 | ContextAssembly state (load relevant context using hierarchical strategy) | 3.4.2.1 State12 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/llm/context.rs with hierarchical context assembly and BFS traversal
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-013 | CodeGeneration state (generate code using Yantra Codex + Multi-LLM consultation) | 3.4.2.1 State13 | Phase 1 - MVP | ✅ | COMPLETE: LLM generation with multi-provider orchestration. Yantra Codex deferred as stretch goal (MVP works without it).
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-014 | DependencyValidation state (validate against dependency graph for breaking changes) | 3.4.2.1 State14 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/agent/validation.rs with GNN-based dependency validation
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-015 | BrowserValidation state (validate UI in actual browser via CDP) | 3.4.2.1 State15 | Phase 1 - MVP | 🟡 | PARTIAL: CDP browser integration exists. Full validation workflow in state machine INCOMPLETE.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-016 | SecurityScanning state (Semgrep, secrets, CVE, license checks) | 3.4.2.1 State16 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/security/scanner.rs with Semgrep, secrets detection, CVE checking
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-017 | ConcurrencyValidation state (detect race conditions, deadlocks, data races) | 3.4.2.1 State17 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No concurrency analysis. Would need ThreadSanitizer/Loom integration.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-018 | FixingIssues state (auto-retry with fixes up to 3 attempts) | 3.4.2.1 State18 | Phase 1 - MVP | ✅ | COMPLETE: Retry logic in agent/orchestrator.rs with auto-fix attempts and confidence scoring
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-019 | FileLockRelease state (release locks on complete/failed) | 3.4.2.1 State19 | Phase 2A - Post-MVP | ⚪ | PLANNED: Paired with FileLockAcquisition in Phase 2A.
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-020 | Complete state (code ready for testing, trigger Testing Machine) | 3.4.2.1 | Phase 1 - MVP | ✅ | COMPLETE: AgentPhase::Complete in agent/state.rs
STATE MACHINES | Code Generation State Machine | STATE MACHINES > Code Generation State Machine | SM-CG-021 | Failed state (human intervention required) | 3.4.2.1 | Phase 1 - MVP | ✅ | COMPLETE: AgentPhase::Failed in agent/state.rs with escalation logic
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-001 | IntentSpecificationExtraction (extract testable specs from user intent - Test Oracle Problem) | 3.4.2.2A State 1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No intent extraction for test oracle. Critical for "what correct means".
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-002 | TestOracleGeneration (spec-based, differential, metamorphic, contract-based strategies) | 3.4.2.2A State 2 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No oracle generation. Tests generated without explicit correctness criteria.
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-003 | InputSpaceAnalysis (boundary values, equivalence partitions, edge cases) | 3.4.2.2A State 3 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No input domain analysis. Would need symbolic execution or constraint solving.
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-004 | TestDataGeneration (valid, invalid, boundary, random test data) | 3.4.2.2A State 4 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No test data generation. Tests use hardcoded values.
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-005 | TestCaseGeneration (generate actual test code with assertions) | 3.4.2.2A State 5 | Phase 1 - MVP | ✅ | COMPLETE: Test generation in src-tauri/src/testing/generator*.rs (Python pytest, JS jest)
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-006 | AssertionStrengthAnalysis (verify assertions are strong, not weak like "is not None") | 3.4.2.2A State 6 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No assertion quality checking. Weak assertions may pass through.
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-007 | TestQualityVerification (mutation testing for effectiveness, >80% mutation score) | 3.4.2.2A State 7 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No mutation testing. Would need mutmut or stryker integration.
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-008 | TestSuiteOrganization (organize by module/feature, separate unit/integration/E2E) | 3.4.2.2A State 8 | Phase 1 - MVP | ✅ | COMPLETE: Test generators create organized test files with proper structure
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-009 | TestImpactAnalysis (determine affected tests from code changes via GNN) | 3.4.2.2A State 9 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/agent/affected_tests.rs with GNN-based impact analysis
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-010 | TestUpdateGeneration (generate test updates when code changes - test-code co-evolution) | 3.4.2.2A State 10 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: Tests don't auto-update with code changes. Manual sync required.
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-011 | Complete state (high-quality test suite ready for execution) | 3.4.2.2A | Phase 1 - MVP | ✅ | COMPLETE: Success state exists
STATE MACHINES | Test Intelligence State Machine | STATE MACHINES > Test Intelligence State Machine | SM-TI-012 | Failed state (unable to generate effective tests) | 3.4.2.2A | Phase 1 - MVP | ✅ | COMPLETE: Failure state with escalation
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-001 | EnvironmentSetup (create venv, install test deps, parallel setup) | 3.4.2.2B State 1 | Phase 1 - MVP | ✅ | COMPLETE: Environment setup in agent/environment.rs with parallel dependency installation
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-002 | FlakeDetectionSetup (configure flaky test detection, 3 runs per test) | 3.4.2.2B State 2 | Phase 1 - MVP | 🟡 | PARTIAL: Retry logic exists in testing/retry.rs. Flakiness scoring (3 runs) NOT fully implemented.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-003 | UnitTesting (pytest/jest with coverage, execution tracing, parallel 4+ workers) | 3.4.2.2B State 3 | Phase 1 - MVP | ✅ | COMPLETE: testing/executor.rs (pytest) and executor_js.rs (jest) with coverage support
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-004 | IntegrationTesting (API integrations, databases, contract validation, parallel) | 3.4.2.2B State 4 | Phase 1 - MVP | 🟡 | PARTIAL: Test execution supports integration tests. Contract validation INCOMPLETE.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-005 | BrowserTesting (Playwright E2E for user workflows, parallel 2-3 browsers) | 3.4.2.2B State 5 | Phase 1 - MVP | 🟡 | PARTIAL: CDP browser exists. Playwright integration MISSING. E2E test orchestration INCOMPLETE.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-006 | PropertyBasedTesting (hypothesis/fast-check for property tests, parallel) | 3.4.2.2B State 6 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No property-based testing framework integration.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-007 | ExecutionTraceAnalysis (analyze traces for failures, variable states, call stacks) | 3.4.2.2B State 7 | Phase 1 - MVP | 🟡 | PARTIAL: Test output parsing exists. Full trace analysis (variable states) INCOMPLETE.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-008 | FlakeDetectionAnalysis (identify and quarantine flaky tests, flakiness score >0.3) | 3.4.2.2B State 8 | Phase 1 - MVP | 🟡 | PARTIAL: Retry detection exists. Flakiness scoring and quarantine logic INCOMPLETE.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-009 | CoverageAnalysis (check coverage metrics, >80% target) | 3.4.2.2B State 9 | Phase 1 - MVP | ✅ | COMPLETE: Coverage tracking in test executors with threshold checking
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-010 | SemanticCorrectnessVerification (verify tests match intent, detect tautological asserts) | 3.4.2.2B State 10 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No semantic verification. Tautological tests (assert x == x) may pass.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-011 | ErrorClassification (code bug, test bug, environmental, flaky, timeout) | 3.4.2.2B State 11 | Phase 1 - MVP | ✅ | COMPLETE: testing/runner.rs with FailureType enum (CodeBug, TestBug, Environmental, Timeout)
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-012 | FixingIssues (auto-retry with fixes for test failures) | 3.4.2.2B State 12 | Phase 1 - MVP | ✅ | COMPLETE: Retry executor in testing/retry.rs with auto-fix attempts
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-013 | TestCodeCoEvolutionCheck (verify tests aligned with code after changes) | 3.4.2.2B State 13 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No test-code synchronization checking. Tests may become stale.
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-014 | Complete state (all tests pass, adequate coverage, semantic correctness verified) | 3.4.2.2B | Phase 1 - MVP | ✅ | COMPLETE: Success state in test execution flow
STATE MACHINES | Test Execution State Machine | STATE MACHINES > Test Execution State Machine | SM-TE-015 | Failed state (tests failed after max retries) | 3.4.2.2B | Phase 1 - MVP | ✅ | COMPLETE: Failure state with escalation to human
STATE MACHINES | Deployment State Machine | STATE MACHINES > Deployment State Machine | SM-DEP-001 | PackageBuilding (Docker image or build artifacts, parallel multi-stage) | 3.4.2.3 State 1 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/agent/packaging.rs with Docker and Python package builders
STATE MACHINES | Deployment State Machine | STATE MACHINES > Deployment State Machine | SM-DEP-002 | ConfigGeneration (railway.json, Dockerfile, env config, parallel) | 3.4.2.3 State 2 | Phase 1 - MVP | 🟡 | PARTIAL: Dockerfile generation exists. Railway.json and comprehensive env config INCOMPLETE.
STATE MACHINES | Deployment State Machine | STATE MACHINES > Deployment State Machine | SM-DEP-003 | RailwayUpload (push to Railway.app, parallel artifact/layer upload) | 3.4.2.3 State 3 | Phase 1 - MVP | 🟡 | PARTIAL: agent/deployment.rs has deployment logic. Railway API integration INCOMPLETE.
STATE MACHINES | Deployment State Machine | STATE MACHINES > Deployment State Machine | SM-DEP-004 | HealthCheck (verify service responding, parallel endpoint checks) | 3.4.2.3 State 4 | Phase 1 - MVP | 🟡 | PARTIAL: Health check logic exists. Parallel endpoint checking INCOMPLETE.
STATE MACHINES | Deployment State Machine | STATE MACHINES > Deployment State Machine | SM-DEP-005 | RollbackOnFailure (auto-rollback if health check fails) | 3.4.2.3 State 5 | Phase 1 - MVP | 🟡 | PARTIAL: Rollback logic exists. Full automation INCOMPLETE.
STATE MACHINES | Deployment State Machine | STATE MACHINES > Deployment State Machine | SM-DEP-006 | Complete state (deployment successful with live URL) | 3.4.2.3 | Phase 1 - MVP | ✅ | COMPLETE: Success state in deployment flow
STATE MACHINES | Deployment State Machine | STATE MACHINES > Deployment State Machine | SM-DEP-007 | Failed state (deployment failed, rollback triggered) | 3.4.2.3 | Phase 1 - MVP | ✅ | COMPLETE: Failure state with rollback trigger
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-001 | LiveMonitoring (continuous production monitoring: errors, performance, API response, parallel) | 3.4.2.4 State 1 | Phase 4 - Post-MVP | ⚪ | PLANNED: Real-time monitoring with <1s detection. Phase 4 self-healing feature.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-002 | BrowserValidation (Real User Monitoring with session replay, parallel sessions) | 3.4.2.4 State 2 | Phase 4 - Post-MVP | ⚪ | PLANNED: RUM integration in Phase 4.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-003 | ErrorAnalysis (pattern matching, severity classification, parallel patterns) | 3.4.2.4 State 3 | Phase 4 - Post-MVP | ⚪ | PLANNED: AI-driven error analysis in production.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-004 | IssueDetection (dependency graph tracing, blast radius, parallel paths) | 3.4.2.4 State 4 | Phase 4 - Post-MVP | ⚪ | PLANNED: GNN-based production issue detection.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-005 | AutoFixGeneration (LLM generates fix candidates, parallel candidates) | 3.4.2.4 State 5 | Phase 4 - Post-MVP | ⚪ | PLANNED: Automatic fix generation for production issues.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-006 | FixValidation (test in staging using CodeGen + Testing machines) | 3.4.2.4 State 6 | Phase 4 - Post-MVP | ⚪ | PLANNED: Staging environment validation before production deploy.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-007 | CICDPipeline (automated deployment of fix, parallel deployment) | 3.4.2.4 State 7 | Phase 4 - Post-MVP | ⚪ | PLANNED: CI/CD automation for self-healing.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-008 | VerificationCheck (confirm error rate drops, parallel regions) | 3.4.2.4 State 8 | Phase 4 - Post-MVP | ⚪ | PLANNED: Post-deployment verification across regions.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-009 | LearningUpdate (update Yantra Codex with pattern, parallel stores) | 3.4.2.4 State 9 | Phase 4 - Post-MVP | ⚪ | PLANNED: Learn from production incidents.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-010 | Active state (normal monitoring, no incidents) | 3.4.2.4 State 10 | Phase 4 - Post-MVP | ⚪ | PLANNED: Steady-state monitoring.
STATE MACHINES | Maintenance State Machine (Phase 4) | STATE MACHINES > Maintenance State Machine (Phase 4) | SM-MNT-011 | Incident state (active incident being handled) | 3.4.2.4 State 11 | Phase 4 - Post-MVP | ⚪ | PLANNED: Incident response automation.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-001 | DocumentationAnalysis (analyze what docs needed based on triggers) | 3.4.2.5 State 1 | Phase 2 - Post-MVP | ⚪ | PLANNED: Auto-detect documentation needs from code changes/requirements.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-002 | BlockIdentification (identify YDoc blocks to create/update) | 3.4.2.5 State 2 | Phase 2 - Post-MVP | ⚪ | PLANNED: Map changes to YDoc blocks.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-003 | ContentGeneration (generate/update documentation content using LLM) | 3.4.2.5 State 3 | Phase 2 - Post-MVP | ⚪ | PLANNED: LLM-driven documentation generation.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-004 | GraphLinking (create traceability edges in dependency graph) | 3.4.2.5 State 4 | Phase 2 - Post-MVP | ⚪ | PLANNED: Link documentation to code/tests/requirements in GNN.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-005 | ConflictDetection (check for duplicate/conflicting docs, SSOT validate) | 3.4.2.5 State 5 | Phase 2 - Post-MVP | ⚪ | PLANNED: SSOT validation for documentation.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-006 | UserClarification (request user input for conflicts) | 3.4.2.5 State 6 | Phase 2 - Post-MVP | ⚪ | PLANNED: Human-in-loop for conflict resolution.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-007 | ConflictResolution (apply resolution or auto-resolve simple conflicts) | 3.4.2.5 State 7 | Phase 2 - Post-MVP | ⚪ | PLANNED: Automatic conflict resolution where possible.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-008 | Validation (verify documentation quality and completeness) | 3.4.2.5 State 8 | Phase 2 - Post-MVP | ⚪ | PLANNED: Documentation quality checks.
STATE MACHINES | Documentation Governance State Machine (Phase 2) | STATE MACHINES > Documentation Governance State Machine (Phase 2) | SM-DOC-009 | Complete state (documentation updated and synced) | 3.4.2.5 | Phase 2 - Post-MVP | ⚪ | PLANNED: Success state for documentation governance.
SHARED SERVICES | CreationValidation Service | SHARED SERVICES > CreationValidation Service | SVC-001 | Path check validation (prevent exact file path duplicates) | 3.4.3.1 | Phase 1 - MVP | ✅ | COMPLETE: File operations check existence before creation
SHARED SERVICES | CreationValidation Service | SHARED SERVICES > CreationValidation Service | SVC-002 | Name check validation (prevent function/class name duplicates in scope) | 3.4.3.1 | Phase 1 - MVP | 🟡 | PARTIAL: GNN tracks symbols. Duplicate name checking during generation INCOMPLETE.
SHARED SERVICES | CreationValidation Service | SHARED SERVICES > CreationValidation Service | SVC-003 | Semantic check validation (detect semantic duplicates, >0.85 similarity) | 3.4.3.1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No semantic similarity checking during creation. Embeddings exist but not used for this.
SHARED SERVICES | CreationValidation Service | SHARED SERVICES > CreationValidation Service | SVC-004 | Dependency check validation (functional duplicates: same imports + logic) | 3.4.3.1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No functional duplicate detection during creation.
SHARED SERVICES | CreationValidation Service | SHARED SERVICES > CreationValidation Service | SVC-005 | De-duplication index (vector DB for similarity search with content hashes) | 3.4.3.1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No content-addressable storage or dedup index.
SHARED SERVICES | CreationValidation Service | SHARED SERVICES > CreationValidation Service | SVC-006 | Resolution options (present reuse/update/create options to user/agent) | 3.4.3.1 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No duplicate resolution workflow.
SHARED SERVICES | Browser Validation Service | SHARED SERVICES > Browser Validation Service | SVC-007 | Browser launch (Chrome/Chromium/Edge via CDP) | 3.4.3.2 | Phase 1 - MVP | ✅ | COMPLETE: src-tauri/src/browser/cdp.rs with browser launch via chromiumoxide
SHARED SERVICES | Browser Validation Service | SHARED SERVICES > Browser Validation Service | SVC-008 | Navigation (navigate to localhost URLs) | 3.4.3.2 | Phase 1 - MVP | ✅ | COMPLETE: Navigation implemented in CDP module
SHARED SERVICES | Browser Validation Service | SHARED SERVICES > Browser Validation Service | SVC-009 | Scenario execution (clicks, fills, verification) | 3.4.3.2 | Phase 1 - MVP | 🟡 | PARTIAL: Basic CDP commands available. Full scenario orchestration INCOMPLETE.
SHARED SERVICES | Browser Validation Service | SHARED SERVICES > Browser Validation Service | SVC-010 | Console error capture (monitor and capture JavaScript errors) | 3.4.3.2 | Phase 1 - MVP | 🟡 | PARTIAL: Console event monitoring exists. Error collection and reporting INCOMPLETE.
SHARED SERVICES | Browser Validation Service | SHARED SERVICES > Browser Validation Service | SVC-011 | Screenshot capture (take screenshots for visual verification) | 3.4.3.2 | Phase 1 - MVP | ✅ | COMPLETE: Screenshot API in browser/cdp.rs with PNG capture
SHARED SERVICES | Browser Validation Service | SHARED SERVICES > Browser Validation Service | SVC-012 | Performance monitoring (load time, FPS, performance metrics) | 3.4.3.2 | Phase 1 - MVP | 🟡 | PARTIAL: CDP performance events available. Metrics collection and analysis INCOMPLETE.
SHARED SERVICES | SSOT Validation Service | SHARED SERVICES > SSOT Validation Service | SVC-013 | Architecture SSOT (enforce single architecture document per project) | 3.4.3.3 | Phase 1 - MVP | 🟡 | PARTIAL: Architecture storage exists. Multiple architecture prevention INCOMPLETE.
SHARED SERVICES | SSOT Validation Service | SHARED SERVICES > SSOT Validation Service | SVC-014 | Requirements SSOT (enforce single requirements doc per epic/feature) | 3.4.3.3 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No requirements document enforcement.
SHARED SERVICES | SSOT Validation Service | SHARED SERVICES > SSOT Validation Service | SVC-015 | API Specification SSOT (single API spec per endpoint, OpenAPI canon) | 3.4.3.3 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No API specification tracking or SSOT enforcement.
SHARED SERVICES | SSOT Validation Service | SHARED SERVICES > SSOT Validation Service | SVC-016 | SSOT conflict resolution (user chooses primary when multiple found) | 3.4.3.3 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No conflict resolution workflow for SSOT violations.
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-001 | File explorer (browse project files with folder structure) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/FileTree.tsx with hierarchical file browser
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-002 | Monaco code editor (syntax highlighting, autocomplete, errors) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/CodeViewer.tsx with full Monaco integration
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-003 | Chat/Task interface (natural language input for tasks) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/ChatPanel.tsx with LLM integration
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-004 | Dependency view (visualize dependency graph relationships) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/DependencyGraph.tsx with Cytoscape.js visualization
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-005 | Architecture view (display/edit architecture diagrams) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/ArchitectureView.tsx (referenced in specs, needs verification)
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-006 | Documentation view (4-panel: Features/Decisions/Changes/Tasks) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/DocumentationPanels.tsx with multi-panel layout
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-007 | Browser preview (CDP-based live preview in system browser) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/BrowserPreview.tsx integrated with CDP backend
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-008 | Terminal view (integrated terminal for command execution) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/Terminal.tsx and MultiTerminal.tsx with xterm.js
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-009 | SolidJS reactive UI (fast, reactive framework) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: Entire UI built with SolidJS, signals for reactivity
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-010 | TailwindCSS styling (utility-first CSS framework) | 3.1 Layer 5 | Phase 1 - MVP | ✅ | COMPLETE: Tailwind configured and used throughout UI components
USER INTERFACE | Core UI Components | USER INTERFACE > Core UI Components | UI-011 | Real-time WebSocket (live updates from backend) | 3.1 Layer 5 | Phase 1 - MVP | 🟡 | PARTIAL: Tauri event system for backend communication. Full WebSocket pubsub INCOMPLETE.
USER INTERFACE | Progress & Feedback | USER INTERFACE > Progress & Feedback | UI-012 | State machine progress bars (CodeGen, Testing, Deployment) | 3.4.2G | Phase 1 - MVP | ✅ | COMPLETE: src-ui/components/ProgressIndicator.tsx with state visualization
USER INTERFACE | Progress & Feedback | USER INTERFACE > Progress & Feedback | UI-013 | Work visibility indicators (show which files being modified) | 3.1.3 | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No active file modification UI indicators.
USER INTERFACE | Progress & Feedback | USER INTERFACE > Progress & Feedback | UI-014 | Blast radius preview (show impact before executing changes) | 3.4.2.1A | Phase 1 - MVP | ❌ | NOT IMPLEMENTED: No blast radius visualization in UI.
USER INTERFACE | Progress & Feedback | USER INTERFACE > Progress & Feedback | UI-015 | Real-time state updates (show current state names and transitions) | 3.4.2G | Phase 1 - MVP | 🟡 | PARTIAL: Progress indicator shows states. Real-time transition updates INCOMPLETE.
USER INTERFACE | Progress & Feedback | USER INTERFACE > Progress & Feedback | UI-016 | Confidence scores (display confidence scores for generated code) | 3.4.1 | Phase 1 - MVP | 🟡 | PARTIAL: Confidence scoring in backend. UI display INCOMPLETE.
ADVANCED FEATURES (POST-MVP) | Team of Agents (Phase 2A) | ADVANCED FEATURES (POST-MVP) > Team of Agents (Phase 2A) | ADV-001 | Lead agent implementation (task decomposition and assignment coordinator) | 3.4.5.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Master agent for team coordination in Phase 2A.
ADVANCED FEATURES (POST-MVP) | Team of Agents (Phase 2A) | ADVANCED FEATURES (POST-MVP) > Team of Agents (Phase 2A) | ADV-002 | Specialist agents (Coding, Architecture, Testing, Documentation, UX) | 3.4.5.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Domain-specialized agents with configurable LLMs.
ADVANCED FEATURES (POST-MVP) | Team of Agents (Phase 2A) | ADVANCED FEATURES (POST-MVP) > Team of Agents (Phase 2A) | ADV-003 | Git coordination branch (append-only event log in .yantra/coordination) | 3.4.5.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Git-based coordination for agent communication.
ADVANCED FEATURES (POST-MVP) | Team of Agents (Phase 2A) | ADVANCED FEATURES (POST-MVP) > Team of Agents (Phase 2A) | ADV-004 | A2A protocol (agent-to-agent communication for dependencies) | 3.4.5.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Inter-agent communication protocol.
ADVANCED FEATURES (POST-MVP) | Team of Agents (Phase 2A) | ADVANCED FEATURES (POST-MVP) > Team of Agents (Phase 2A) | ADV-005 | Agent instruction files (per-agent config in .yantra/agents/) | 3.4.5.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Customizable agent behavior via instruction files.
ADVANCED FEATURES (POST-MVP) | Team of Agents (Phase 2A) | ADVANCED FEATURES (POST-MVP) > Team of Agents (Phase 2A) | ADV-006 | Configurable agent LLMs (each agent can use different LLM) | 3.4.5.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: Domain-optimized LLM selection per agent.
ADVANCED FEATURES (POST-MVP) | Team of Agents (Phase 2A) | ADVANCED FEATURES (POST-MVP) > Team of Agents (Phase 2A) | ADV-007 | Parallel agent execution (3-10 agents working simultaneously) | 3.4.5.1 | Phase 2A - Post-MVP | ⚪ | PLANNED: 3-10x speedup through parallel agent execution.
ADVANCED FEATURES (POST-MVP) | Cloud Graph Database (Phase 2B) | ADVANCED FEATURES (POST-MVP) > Cloud Graph Database (Phase 2B) | ADV-008 | Tier 0 cloud storage (shared dependency graph: Redis + PostgreSQL) | 3.4.5.2 | Phase 2B - Post-MVP | ⚪ | PLANNED: Cross-machine coordination via cloud graph database.
ADVANCED FEATURES (POST-MVP) | Cloud Graph Database (Phase 2B) | ADVANCED FEATURES (POST-MVP) > Cloud Graph Database (Phase 2B) | ADV-009 | Level 2 direct dep detection (warn about direct dependency conflicts) | 3.4.5.2 | Phase 2B - Post-MVP | ⚪ | PLANNED: Proactive warnings for direct dependency conflicts.
ADVANCED FEATURES (POST-MVP) | Cloud Graph Database (Phase 2B) | ADVANCED FEATURES (POST-MVP) > Cloud Graph Database (Phase 2B) | ADV-010 | Level 3 transitive dep detection (warn about transitive conflicts) | 3.4.5.2 | Phase 2B - Post-MVP | ⚪ | PLANNED: Deep conflict detection through transitive deps.
ADVANCED FEATURES (POST-MVP) | Cloud Graph Database (Phase 2B) | ADVANCED FEATURES (POST-MVP) > Cloud Graph Database (Phase 2B) | ADV-011 | Level 4 semantic dep detection (warn about function signature changes) | 3.4.5.2 | Phase 2B - Post-MVP | ⚪ | PLANNED: API-level conflict detection.
ADVANCED FEATURES (POST-MVP) | Cloud Graph Database (Phase 2B) | ADVANCED FEATURES (POST-MVP) > Cloud Graph Database (Phase 2B) | ADV-012 | Privacy-preserving sync (only sync graph structure, not code content) | 3.4.5.2 | Phase 2B - Post-MVP | ⚪ | PLANNED: Secure cloud sync without exposing code.
ADVANCED FEATURES (POST-MVP) | Cloud Graph Database (Phase 2B) | ADVANCED FEATURES (POST-MVP) > Cloud Graph Database (Phase 2B) | ADV-013 | WebSocket/gRPC protocol (low-latency communication <50ms) | 3.4.5.2 | Phase 2B - Post-MVP | ⚪ | PLANNED: Real-time graph sync with low latency.
ADVANCED FEATURES (POST-MVP) | Cloud Graph Database (Phase 2B) | ADVANCED FEATURES (POST-MVP) > Cloud Graph Database (Phase 2B) | ADV-014 | Per-project isolation (separate graph storage per project) | 3.4.5.2 | Phase 2B - Post-MVP | ⚪ | PLANNED: Multi-project support with isolation.
ADVANCED FEATURES (POST-MVP) | Clean Code Mode (Phase 2C) | ADVANCED FEATURES (POST-MVP) > Clean Code Mode (Phase 2C) | ADV-015 | Dead code detection (detect unused functions, classes, imports, variables) | 3.4.5.3 | Phase 2C - Post-MVP | ⚪ | PLANNED: GNN-based dead code analysis.
ADVANCED FEATURES (POST-MVP) | Clean Code Mode (Phase 2C) | ADVANCED FEATURES (POST-MVP) > Clean Code Mode (Phase 2C) | ADV-016 | Auto-remove threshold (only auto-remove with >80% confidence) | 3.4.5.3 | Phase 2C - Post-MVP | ⚪ | PLANNED: Safe automatic code removal with confidence threshold.
ADVANCED FEATURES (POST-MVP) | Clean Code Mode (Phase 2C) | ADVANCED FEATURES (POST-MVP) > Clean Code Mode (Phase 2C) | ADV-017 | Real-time refactoring (extract duplicates, simplify, rename for clarity) | 3.4.5.3 | Phase 2C - Post-MVP | ⚪ | PLANNED: Continuous code quality improvements.
ADVANCED FEATURES (POST-MVP) | Clean Code Mode (Phase 2C) | ADVANCED FEATURES (POST-MVP) > Clean Code Mode (Phase 2C) | ADV-018 | Component hardening (security, performance, quality, dependency hardening) | 3.4.5.3 | Phase 2C - Post-MVP | ⚪ | PLANNED: Automated component strengthening.
ADVANCED FEATURES (POST-MVP) | Clean Code Mode (Phase 2C) | ADVANCED FEATURES (POST-MVP) > Clean Code Mode (Phase 2C) | ADV-019 | Continuous mode (background process with configurable intervals) | 3.4.5.3 | Phase 2C - Post-MVP | ⚪ | PLANNED: Always-on code maintenance.
ADVANCED FEATURES (POST-MVP) | Enterprise Automation (Phase 3) | ADVANCED FEATURES (POST-MVP) > Enterprise Automation (Phase 3) | ADV-020 | Cross-system intelligence (track external APIs: Stripe, Salesforce) | 3.4.5.4 | Phase 3 - Post-MVP | ⚪ | PLANNED: External API dependency tracking.
ADVANCED FEATURES (POST-MVP) | Enterprise Automation (Phase 3) | ADVANCED FEATURES (POST-MVP) > Enterprise Automation (Phase 3) | ADV-021 | Browser automation full (Playwright integration for legacy systems) | 3.4.5.4 | Phase 3 - Post-MVP | ⚪ | PLANNED: Full browser automation for enterprise integration.
ADVANCED FEATURES (POST-MVP) | Enterprise Automation (Phase 3) | ADVANCED FEATURES (POST-MVP) > Enterprise Automation (Phase 3) | ADV-022 | Self-healing systems (API monitoring, schema drift, auto-migration) | 3.4.5.4 | Phase 3 - Post-MVP | ⚪ | PLANNED: Resilient systems with automatic healing.
ADVANCED FEATURES (POST-MVP) | Enterprise Automation (Phase 3) | ADVANCED FEATURES (POST-MVP) > Enterprise Automation (Phase 3) | ADV-023 | Multi-language support (JavaScript/TypeScript parser, cross-lang deps) | 3.4.5.4 | Phase 3 - Post-MVP | ⚪ | PLANNED: Polyglot codebase support beyond Python.
ADVANCED FEATURES (POST-MVP) | Enterprise Automation (Phase 3) | ADVANCED FEATURES (POST-MVP) > Enterprise Automation (Phase 3) | ADV-024 | Enterprise features (multitenancy, user accounts, team collab, billing) | 3.4.5.4 | Phase 3 - Post-MVP | ⚪ | PLANNED: Enterprise-ready platform features.
ADVANCED FEATURES (POST-MVP) | Platform Maturity (Phase 4) | ADVANCED FEATURES (POST-MVP) > Platform Maturity (Phase 4) | ADV-025 | Performance optimization (GNN queries <100ms for 100k+ LOC, dist GNN) | 3.4.5.5 | Phase 4 - Post-MVP | ⚪ | PLANNED: Scalability for large codebases.
ADVANCED FEATURES (POST-MVP) | Platform Maturity (Phase 4) | ADVANCED FEATURES (POST-MVP) > Platform Maturity (Phase 4) | ADV-026 | Advanced refactoring (architectural refactoring: monolith → microservices) | 3.4.5.5 | Phase 4 - Post-MVP | ⚪ | PLANNED: Large-scale architectural transformations.
ADVANCED FEATURES (POST-MVP) | Platform Maturity (Phase 4) | ADVANCED FEATURES (POST-MVP) > Platform Maturity (Phase 4) | ADV-027 | Plugin ecosystem (plugin system, marketplace, CLI, REST API, SDKs) | 3.4.5.5 | Phase 4 - Post-MVP | ⚪ | PLANNED: Extensibility through plugins and APIs.
ADVANCED FEATURES (POST-MVP) | Platform Maturity (Phase 4) | ADVANCED FEATURES (POST-MVP) > Platform Maturity (Phase 4) | ADV-028 | Enterprise deployment (on-premise, air-gapped, private cloud, SLAs) | 3.4.5.5 | Phase 4 - Post-MVP | ⚪ | PLANNED: Enterprise deployment options.